## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Susma | Irvin | Brandon | Alex | Thian | Jack | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 2 |  | 3
|  | Design architecture | Software Engineer | Irvin, Alex, Brandon | 2 |  | 3 |  |  | 3 | 3 | 3 |  |  | 9
| Requirements |  |  |  |  | 9 |  | 4 | [6 empty] | 0
|  | Gather | Requirements Engineer | Jack, Alex | 2 |  | 1 |  |  |  |  | 1 |  | 1 | 2
|  | Analyze | Requirements Engineer | Jack, Alex | 4 |  | 2 |  |  |  |  | 2 |  | 2 | 4
|  | Specify | Requirements Engineer | Jack, Alex | 3 |  | 1 |  |  |  |  | 1 |  | 1 | 2
| Documentation |  |  |  |  | 28 |  | 7 | [6 empty] | 0
|  | Project Charter | Requirements Engineer | Jack, Alex | 2 |  | 3 |  |  |  |  | 3 |  | 3 | 6
|  | Release Plan | Project Manager | Jack, Alex | 2 |  | 1 |  |  |  |  | 1 |  | 1 | 2
|  | Requirements Document | Project Manager, Requirements Engineer | Alex, Jack | 5 |  | 1 |  |  |  |  | 1 |  | 1 | 2
|  | Project Plan | Project Manager, Developers | Alex, Irvin, Susma | 5
|  | Architecture Document | Architect | Brandon, Thian, Alex | 4 |  | 2 |  |  |  | 2 | 2 | 2
|  | Test Report | Tester | Brandon, Thian | 8
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Alex, Irvin, Brandon, Jack | 2
Coding | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 62.5 |  | 10
|  | Determine technology needs | Developer | Irvin, Alex, Brandon | 0.5 |  | 0.5 |  |  | 0.5 | 0.5 | 0.5
|  | Research and learn new language and environment | Developer | Brandon, Susma, Jack | 20 |  | 4 |  | 4 |  | 4 |  |  | 4
|  | Set up proxy server software | Developer | Irvin, Alex | 10 |  | 1.5 |  |  | 1.5 | 1.5 | 1.5
|  | Write basic proxy code | Developer | Irvin, Brandon | 5
|  | Implement classes | Developer | Thian, Alex, Brandon | 10 |  | 2 |  |  |  | 2 | 2 | 2
|  | Create HTTP handling code | Developer | Thian, Alex, Brandon | 8 |  | 2 |  |  |  | 2 | 2 | 2
|  | Write code to store user name locally | Developer | Irvin, Alex | 2
|  | Write code for managing HTTP session | Developer | Brandon, Alex | 5
|  | Unit Testing | Developer | Alex, Thian | 2
| Analysis |  |  |  |  | 6 |  | 0
|  | System Testing | Tester | Brandon, Irvin | 2
|  | Bug fix as required | Tester, Developer | Irvin, Brandon | 2
|  | Evaluate needs for next iteration | Project Manager | Alex, Brandon, Irvin | 2 | [9 empty] | 0